## Sprint 1 Backlog
Sprint # | 1
Start on | 2016-09-29 10:50
End on | 2016-10-06 08:00
Demo on | 2016-10-06 08:00
Total Tasks | 17
Day 1 Left | 17
Day 2 Left | 17
Day 3 Left | 16
Day 4 Left | 10
Day 5 Left | 8
Day 6 Left | 8
Day 7 Left | 8
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 | N/A | UML | Documentation | QH | Create initial UML Diagrams | Complete
2 | CRP | Code | Model | QH | Create basic Robot_part class | Complete
3 | CRP | Code | Model | QH | Create derived Head class | Complete
4 | CRP | Code | Model | QH | Create derived Locomotor class | Complete
5 | CRP | Code | Model | QH | Create derived Torso class | Complete
6 | CRP | Code | Model | QH | Create derived Battery class | Complete
7 | CRP | Code | Model | QH | Create derived Arm class | Complete
8 | CRP | Code | Controller | QH | Create Controller class to create random part | Complete
9 | CRP | Code | View | QH | Create Viewer class to view creation of part | Complete
10 | CRP | Code | Testing | QH | Create test code to verify Robot_part and its derived classes work correctly | Not started
11 | DRM | Code | Model | QH | Create Robot_model class | Not started
12 | DRM | Code | View | QH | Update Viewer to support a menu that creates robot parts and a robot model | Not started
13 | DRM | Code | Controller | QH | Update Controller to execute menu commands | Not started
14 | DRM | Code | Testing | QH | Update test code to also verify that Robot_model works correctly | Not started
15 | N/A | UML | Documentation | QH | Update UML Diagrams if needed | Not started
16 | CRP | Code | Compilation | QH | Create Makefile for assembling program | Incomplete
17 | DRM | Code | Compilation | QH | Update Makefile for assembling Robot_Model as well | Not started
0 | 17
1 | 17
2 | 17
3 | 16
4 | 10
5 | 8
6 | 8
7 | 8

## Sprint 2 Backlog
Sprint # | 2
Start on | 2016-10-06 08:00
End on | 2016-10-13 08:00
Demo on | 2016-10-13 08:00
Total Tasks | 16
Day 1 Left | 16
Day 2 Left | 16
Day 3 Left | 16
Day 4 Left | 15
Day 5 Left | 14
Day 6 Left | 8
Day 7 Left | 6
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
0 | N/A | UML | Documentation | QH | Update UML Diagrams for features DRM, LRM, and RO | Complete
1 | CRP | Code | Testing | QH | Create test code to verify Robot_part and its derived classes work correctly | Complete
2 | DRM | Code | Model | QH | Create Robot_model class | Complete
5 | DRM | Code | Testing | QH | Update test code to also verify that Robot_model works correctly | Complete
6 | CRP | Code | Compilation | QH | Fix program so that it compiles correctly | Complete
7 | DRM | Code | Compilation | QH | Update Makefile for assembling Robot_Model as well | Complete
8 | LRM | Code | View | QH | Update Viewer class's menu to add an option to list robot models | Not started
9 | LRM | Code | Controller | QH | Update Controller to execute the command that lists robot models | Not started
10 | LRM | Code | Testing | QH | Update test code to verify that the listing function works correctly | Not started
11 | DRM | Code | Model | QH | Create Shop class to handle robot models and robot parts | Complete | Needs to manage current parts and models, as well as provide functions to execute future menu cmds
12 | DRM | Code | Model | QH | Update main function to execute program | Not started | see updated UML
13 | DRM | Code | Controller | QH | Update Controller class to interact with Shop class and execute menu commands | Not started | see updated UML; Need to list robots models, then list parts in selected model
14 | DRM | Code | View | QH | Update View class to interact with Shop class and support a menu that creates robot parts and robot models | Not started | see updated UML
15 | N/A | UML | Documentation | QH | Update UML Diagrams if needed | Complete
16 | DRM | Code | Model | QH | Update Makefile for assembling Shop as well | Complete
17 | DRM | Code | Testing | QH | Update test code to verify that Shop works correctly | Complete
0 | 16
1 | 16
2 | 16
3 | 16
4 | 15
5 | 14
6 | 8
7 | 6

## Sprint 3 Backlog
Sprint # | 3
Start on | 2016-10-13 08:00
End on | 2016-10-20 08:00
Demo on | 2016-10-20 08:00
Total Tasks | 13
Day 1 Left | 10
Day 2 Left | 10
Day 3 Left | 4
Day 4 Left | 4
Day 5 Left | 3
Day 6 Left | 3
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
0 | LRM | Code | View | QH | Update Viewer class's menu to add an option to list robot models | Complete
1 | LRM | Code | Controller | QH | Update Controller to execute the command that lists robot models | Complete | Need to list robots models, then list parts in selected model
3 | DRM | Code | Model | QH | Update main function to execute program | Complete | see updated UML
4 | DRM | Code | Controller | QH | Update Controller class to interact with Shop class and execute menu commands | Complete | see updated UML
5 | DRM | Code | View | QH | Update View class to interact with Shop class and support a menu that creates robot parts and robot models | Complete | see updated UML
6 | N/A | UML | Documentation | QH | Update UML Diagrams if needed | Complete
7 | N/A | Code | Testing | QH | Update test code for any new functions not in View or Controller or main() | Complete | as needed
10 | RO | Code | Controller | QH | Update Controller to execute the robot-model-ordering command | Complete
11 | RO | Code | View | QH | Update Robot_Model class to include prices | Complete
13 | N/A | Other | Documentation | QH | Create a brief user manual | Complete | needs to be a few paragraphs long
14 | N/A | Other | Marketing | QH | Create sales material to increase the probability of winning Shop contract | Complete | can be a PowerPoint, PDF Brochure, YouTube video, etc.
16 | N/A | Other | Submission | QH | Finalize the UML Diagrams, git repository, user manual, sales material, and source code for submission | Complete | ensure that UML Diagrams properly reflect the program
18 | N/A | Other | Documentation | QH | Proofread user manual | Complete
0 | 13
1 | 10
2 | 10
3 | 4
4 | 4
5 | 3
6 | 3
7 | 0

## Sprint 4 Backlog
Sprint # | 4
Start on | 2016-10-20 08:00
End on | 2016-10-27 08:00
Demo on | 2016-10-27 08:00
Total Tasks | 2
Day 1 Left | 2
Day 2 Left | 2
Day 3 Left | 2
Day 4 Left | 2
Day 5 Left | 2
Day 6 Left | 1
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
0 | N/A | Preparation | Install | QH | Install FLTK | Complete | v1.3
1 | N/A | Preparation | Studying | QH | Study for Exam 2 | Complete
0 | 2
1 | 2
2 | 2
3 | 2
4 | 2
5 | 2
6 | 1
7 | 0

## Sprint 5 Backlog
Sprint # | 5
Start on | 2016-10-27 08:00
End on | 2016-11-03 08:00
Demo on | 2016-11-03 08:00
Total Tasks | 8
Day 1 Left | 8
Day 2 Left | 8
Day 3 Left | 7
Day 4 Left | 5
Day 5 Left | 4
Day 6 Left | 0
Day 7 Left | 0
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
0 | N/A | Documentation | UML | QH | Update the UML Diagrams for the new features to be implemented | Complete | Updated for GUI approach
0.5 | N/A | Backup | git | QH | Set up git repository for Homework 6 | Complete
1 | GUIW | Code | Main | QH | Create Fl_Window | Complete
2 | GUIW | Code | Main | QH | Create a random part | Complete
3 | GUIW | Code | Main | QH | Add dialog box stating displaying the random part created | Complete
4 | GUIW | Code | Main | QH | Add necessary code to display window and run FLTK | Complete
5 | GUIW | Code | Makefile | QH | Create new Makefile to correctly compile a FLTK program | Complete
6 | N/A | Preparation | Install | QH | Get FLTK to correctly compile on machine | Complete
0 | 8
1 | 8
2 | 8
3 | 7
4 | 5
5 | 4
6 | 0
7 | 0

## Sprint 6 Backlog
Sprint # | 6
Start on | 2016-11-03 08:00
End on | 2016-11-10 08:00
Demo on | 2016-11-10 08:00
Total Tasks | 9
Day 1 Left | 9
Day 2 Left | 6
Day 3 Left | 6
Day 4 Left | 6
Day 5 Left | 3
Day 6 Left | 3
Day 7 Left | 1
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
0 | CRP-G | Code | Main | QH | Create a menu bar | Complete
1 | CRP-G | Code | Main | QH | Create a menu bar item with a submenu option to create a robot part | Complete | Menu title: "Create"; Submenu title: "Robot Part"
2 | CRP-G | Code | Controller | QH | Create a class that will call Fl_input dialogs to collect robot part info | Complete
3 | CRP-G | Code | Main | QH | Create a callback for Create>Robot Part that calls aforementioned dialog | Complete
4 | CRP-G | Code | Makefile | QH | Update Makefile as needed | Complete
5 | DRM-G | Code | Main | QH | Create new submenu option under Create for a Robot Model | Complete
6 | DRM-G | Code | Controller | QH | Create a function that will call Fl_input dialogs to collect robot model info | Incomplete
7 | DRM-G | Code | Main | QH | Create a callback for Create>Robot Model that calls aforementioned dialog | Complete
8 | DRM-G | Code | Makefile | QH | Update Makefile as needed | Complete
0 | 9
1 | 9
2 | 6
3 | 6
4 | 6
5 | 3
6 | 3
7 | 1

## Sprint 7 Backlog
Sprint # | 7
Start on | 2016-11-10 08:00
End on | 2016-11-17 08:00
Demo on | 2016-11-17 08:00
Total Tasks | 7
Day 1 Left | 5
Day 2 Left | 3
Day 3 Left | 3
Day 4 Left | 3
Day 5 Left | 3
Day 6 Left | 3
Day 7 Left | 1
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
0 | DRM-G | Code | Main | QH | Create a class that will call Fl_input dialogs to collect robot model info | Complete
1 | LRM-G | Code | Main | QH | Create a class that will output current robot model info | Incomplete
2 | LRM-G | Code | Main | QH | Add methods for extracting information | Complete
3 | LRM-G | Code | Main | QH | Design callbacks for widgets in listing class | Complete
4 | LRM-G | Code | Main | QH | Add menu option for listing robot models | Complete | Menu option: Report > All Robot Models
5 | DRM-G | Code | Debug | QH | Create debug option to generate random robot parts | Complete
6 | LRM-G | Code | Debug | QH | Create debug option to generate random robot models | Complete
0 | 7
1 | 5
2 | 3
3 | 3
4 | 3
5 | 3
6 | 3
7 | 1

## Product Backlog
Product Name: | Robbie Robot Shop Manager
Team ID:
Name: | Quinton Helton
Initials: | QH
Student ID: | 1001263156
(Additional names for teams only)
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Total Features | 36 | Status | Sprint Ends
Sprint 1 Left | 36 | Completed | 2016-10-06
Sprint 2 Left | 35 | Completed | 2016-10-13
Sprint 3 Left | 32 | Completed | 2016-10-20
Sprint 4 Left | 32 | Due | 2016-10-27
Sprint 5 Left | 31 | Due | 2016-11-03
Sprint 6 Left | 30 | Due | 2016-11-10
Sprint 7 Left | 29 | Due | 2016-11-17
Sprint 8 Left | 29 | Due | 2016-11-22
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Prio | Status | Sprint # | Team Size | As a... | I want to... | So that... | Notes
GUIW | 1 | Complete | 5 | 1 | All | open a GUI main window | I can interact with RRS Manager with my mouse | No menu required here – run program, create a part
CRP | 2 | Complete | 1 & 2 | 1 | PM | create robot parts | I can define robot models | No menu required here – run program, create a part
CRP-G | 3 | Complete | 6 | 1 | PM | create robot parts via GUI dialogs | I can define robot models | An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
DRM | 4 | Complete | 2 & 3 | 1 | PM | define new robot models | RRS can sell them to our Beloved Customers | Menu needed – create parts, then create a robot model
DRM-G | 5 | Complete | 6 & 7 | 1 | PM | define new robot models via GUI dialogs | RRS can sell them to our Beloved Customers | Similar to robot parts (perhaps Create > Robot Model)
LRM | 6 | Complete | 2 & 3 | 1 | BC | browse a catalog of robots | I can buy one or more robots | Need to list robots models, then list parts in selected model
LRM-G | 7 | Complete | 7 & 8 | 1 | BC | browse a catalog of robots via a GUI report | I can buy one or more robots | A text output is OK initially, but an attractive HTML-like output is desired (perhaps (Report > All Robot Models)
AP-G | 8 | Not started | 8 | 1 | BC | see pictures of the robots in the GUI catalog | I can see what I'm buying | Add picture when defining robot model, and show it in the robot model report
RO | 9 | Complete | 3 | 1 | SA | create a robot order for a Customer | I can sell robots and thus do my job well | Select robot model and quantity, show details with total price
CBC | 10 | Not started | 8 | 1 | PB | Create a new Beloved Customer via GUI | I can keep track of who's buying our products | The usual name, address, phone number, and email address (perhaps Create > Customer)
CSA | 11 | Not started | 8 | 1 | PB | Create a new Sales Associate via GUI | I can keep track of my employees' performance | Name and employee number at a minimum (perhaps Create > Sales Associate)
RO-G | 12 | Not started | 8 | 1 | SA | Create a robot order for a Customer via GUI | I can sell robots and thus do my job well
DP | 13 | Not started |  | 2 | PB | ensure persistence of the RRS data | we don't lose orders or historical data | Write the data to the default filename and reload it next time the program runs
SVD | 14 | Not started |  | 2 | PB | allow the users to save data explicitly via GUI | we can save data without exiting the program | Write the data to the default filename on command (perhaps File > Save to the default filename)
LDD | 15 | Not started |  | 2 | PB | allow the users to load data explicitly via GUI | we can manage multiple stores in different files | Read the data from a user-selected file on command (perhaps File > Open)
SDWN | 16 | Not started |  | 2 | PB | allow the users to save data to a specified name via GUI | we can manage multiple stores in different files | Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
LO | 23 | Not started |  | 2 | PB / SA | view a list of orders per SA | I can estimate the value of employees / I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
LO-G | 24 | Not started |  | 2 | PB / SA | view a report of orders per SA in the GUI | I can estimate the value of employees / I can justify a raise | A basic text report is fine (perhaps Report > Orders by Sales Associate)
LGN | 17 | Not started |  | 3 | All | enable basic login by role and customize the GUI | we don't have options that don't apply to our roles | User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
CPYP | 18 | Not started |  | 3 | All | enable copy and paste from text fields | we can save typing | Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
VB | 21 | Not started |  | 3 | BC | view my bill | I can pay for my robots | Show a BC invoice. Actual payment is outside the scope of this project
VB-G | 22 | Not started |  | 3 | BC | view my bill (invoice) in the GUI | I can pay for my robots | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
VO | 25 | Not started |  | 3 | BC | view my orders | see what I have coming to me | Show list of orders for a BC with total price, then list details of selected order
VO-G | 26 | Not started |  | 3 | BC | view my orders in the GUI | see what I have coming to me | A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
VSR | 27 | Not started |  | 4 | SA | view a sales report | I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
VSR-G | 28 | Not started |  | 4 | SA | view a sales report in the GUI | I can justify a raise | A basic text report is fine (perhaps Report > Orders by Sales Associate)
VLO | 19 | Not started |  | 4 | PB | view a list of orders | I can manage the company | Show list of every order with total price, then list details of selected order
VLO-G | 20 | Not started |  | 4 | PB | view a report of all orders in the GUI | I can manage the company | A basic text report is fine (perhaps Report > All Orders)
UNDO | 29 | Not started |  | 4 | All | Add multi-level undo | Worry less about making mistakes | This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
PC | 30 | Not started |  | 4 | BC | see a pie chart of a model's component costs | I can decide if I want a different model | Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
BRO-G | 31 | Not started |  | Bonus | SA | create a bulk (2+) order for Customer via GUI | avoid proliferation of orders and paperwork | Allow more than one robot model (with respective quantity) on a single order
HRP-G | 32 | Not started |  | Bonus | PM | hide robot parts via GUI | obsolete parts aren't accidentally used | Mark robot parts as “obsolete” and don't allow adding them to new robot models
HRM-G | 33 | Not started |  | Bonus | PM | hide robot models via GUI | obsolete robots aren't ordered | Mark robot models as “obsolete” and don't allow adding them to new orders
SD-G | 34 | Not started |  | Bonus | SA | save a draft order and return to it later via GUI | I can multi-task between indecisive customers | Save an order that hasn't been complete, and allow SA to resume work on it later
BOW | 35 | Not started |  | Extreme Bonus | BC | browse and order robots over the web | I don't have to talk to the Sales Associates! | (Probably can't address until Homework #6)
ADW | 36 | Not started |  | Extreme Bonus | PB | avoid any delays in the RRS web software | my SA team is at maximum productivity | This likely means using threads for key processes (Probably can't address until Homework #6)

## Sprint 8 Backlog
Sprint # | 7
Start on | 2016-11-17 08:00
End on | 2016-11-22 08:00
Demo on | 2016-11-22 08:00
Total Tasks | 27
Day 1 Left | 27
Day 2 Left | 23
Day 3 Left | 14
Day 4 Left | 14
Day 5 Left | 14
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
0 | LRM-G | Code | Main | QH | Finish the listing robot models dialog | Complete
1 | LRM-G | Code | Main | QH | Add a button to see the part information of each listed robot model | Complete
2 | CBC | Code | Model | QH | Create an Address class that stores a street address | Complete
3 | CBC | Code | Model | QH | Create a Customer class and update the Shop class accordingly | Complete
4 | CBC | Code | Main | QH | Add a dialog to create a new beloved customer | Complete
5 | CBC | Code | Main | QH | Add menu option to create a new customer | Complete | New > Customer
6 | CBC | Code | Main | QH | Add functions/callbacks that will extract the information from the customer dialog | Complete
7 | CSA | Code | Model | QH | Create a Sales Associate class and update the Shop class accordingly | Complete
8 | CSA | Code | Main | QH | Add a dialog to create a new sales associate | Complete
9 | CSA | Code | Main | QH | Add menu option to create a new sales associate | Complete | New > Sales Associate
10 | CSA | Code | Main | QH | Add functions/callbacks that will extract the information from the sales associate dialog | Complete
11 | RO-G | Code | Model | QH | Create a Robot Order class and update the Shop class accordingly | Complete
12 | RO-G | Code | Main | QH | Add a dialog to create a new robot order | Incomplete
13 | RO-G | Code | Main | QH | Add menu option to create a new robot order | Complete | New > Robot Order
14 | RO-G | Code | Main | QH | Add function/callbacks that will extract the information from the order dialog | Incomplete
15 | AP-G | Code | Main | QH | Update the dialog that creates robot models to also include an option to choose a picture | Not started
16 | AP-G | Code | Main | QH | Add a new array to main that will store the aforementioned choice of picture | Not started
17 | AP-G | Code | Main | QH | Update the dialog that lists robot models to also display the model's picture | Not started
18 | AP-G | Code | Makefile | QH | Update the Makefile to compile pictures as well | Not started
19 | N/A | Code | Debug | QH | Fix any final bugs in the system | Not started
20 | N/A | Code | Debug | QH | Remove debug options | Not started
21 | N/A | Documentation | UML | QH | Update UML diagrams | Not started
22 | N/A | Documentation | Other | QH | Redo the user manual | Not started
23 | N/A | Documentation | Other | QH | Proofread user manual | Not started
24 | N/A | Marketing | Other | QH | Update sales brochure | Not started
25 | N/A | Marketing | Other | QH | Proofread sales brochure | Not started
26 | N/A | Submission | Other | QH | Finalize the UML Diagrams, git repository, user manual, sales material, and source code for submission | Not started
0 | 27
1 | 27
2 | 23
3 | 14
4 | 14
5 | 14

## Sprint NN Backlog
Sprint # |  |  |  |  | *** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on
Total Tasks | 23
Day 1 Left | 23
Day 2 Left | 23
Day 3 Left | 23
Day 4 Left | 23
Day 5 Left | 23
Day 6 Left | 23
Day 7 Left | 23
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes